{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["教学楼CD报价单20210529 "],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"教学楼CD报价单20210529 ","index":0,"n_rows":25,"n_cols":9,"rows_kept":25,"merged":[[0,0,0,8],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,1,7],[1,8,2,8],[3,1,3,8],[16,1,16,7],[17,0,17,8],[18,0,18,8],[19,0,19,8],[20,0,20,8],[21,0,21,8],[22,0,22,8],[23,0,23,8],[24,0,24,8]],"flags":["formulas_cached_only"]}
["双语学校教学楼CD区公共区域墙面护墙砖粘贴项目报价清单"]
["序号","分部分项名称及项目特征描述","工程量","单位","预估单价（元）",{"$nulls":3},"合价（元）"]
[{"$nulls":4},"主材","辅料","人工","小计"]
["一","施工内容"]
[1,"原有成品保护（1.针对施工位置墙面保护；2：门收边保护；3.地面保护施工墙体向外大于2米。）",1,"项",{"$nulls":3},"*","*"]
[2,"CD公共区域需粘墙砖处墙面处理（1.原乳胶漆墙面基层及面层铲除，铲除至水泥砂浆粉刷基层；2.墙面拉毛处理、墙面刨坑处理；3.墙面满推背胶处理）",4410,"㎡",{"$nulls":3},"*","*"]
[3,"墙砖（规格：300*600mm、品种：陶砖、砖厚度：8mm，砖型、釉面厚度及光泽度不低于学校提供样品、含材料装车费、运费、卸车费，砖到现场卸至学校指定地点）",4410,"㎡",{"$nulls":3},"*","*"]
[4,"CD区墙面墙砖粘贴（墙砖规格：300*600mm、粘贴高度1500mm、含楼梯及楼梯间；施工工艺：水泥掺801胶粘贴、密拼粘贴、含门窗等成品保护措施；现场情况：走廊门洞、水井、电井、等洞口较多）",4410,"㎡",{"$nulls":3},"*","*"]
[5,"不锈钢收边条（规格：15*15mm“L”型、材质：0.7mm厚304白色拉丝不锈钢）产品质量不得低于学校指定样品",4980,"m",{"$nulls":3},"*","*"]
[6,"不锈钢收边条（规格：20*20mm“L”型、材质：0.7mm厚304白色拉丝不锈钢）产品质量不得低于学校指定样品",200,"m",{"$nulls":3},"*","*"]
[7,"瓷砖上沿及墙体阳角处“L”型不锈钢收边条安装（结构胶粘贴安装、阳角转角处做防伤害处理）",5180,"m",{"$nulls":3},"*","*"]
[8,"墙砖上沿不锈钢与墙面结合处密封胶打胶处理、门窗洞口处墙砖与门窗结合处密封胶打胶（胶采用三棵树牌高强度中型结构胶）",5800,"m",{"$nulls":3},"*","*"]
[9,"材料运输、上楼（墙砖、水泥、胶、收边条等，其中墙砖由学校指定区域运至施工现场）",1,"项",{"$nulls":3},"*","*"]
[10,"施工垃圾下楼、外运、保洁",1,"项",{"$nulls":3},"*","*"]
[11,"原踢脚线拆除（保护性拆除原踢脚线并归置、下楼、运至学校指定地点）",1,"项",{"$nulls":3},"*","*"]
[12,"施工区域墙上已安装文化展板保护性拆除及重新安装",50,"套",{"$nulls":3},"*","*"]
[null,"工程费合计（含税金）",{"$nulls":6},"*"]
["相关说明及要求"]
["1.本工程采用项目大包干的方式，即：包材料（含辅料）、包施工、包质量、包工期、包安全、包检测、包验收合格。        \n"]
["2.本工程价款已包括人工费、材料费、机械消耗费（搭架等）、其他直接费、间接费、利润、税金和施工技术措施费、质检部门规定的各种检测项目费用等全部施工费用。"]
["3.工程所用材料包括相关辅料等必须符合国家有关标准，有相关资质。"]
["4.投标人所在公司需有相关资质，但本项目开票可另行采用个人或者小规模公司开具3-5％的普通发票。"]
["5.报价清单中“*”为必填项目，上述工程量为预估，保持项目单价不变，项目合同总价按学校组织验收结果据实结算。"]
["6.本项目没有预付款，项目整体质保2年，乙方按学校要求及规范施工，项目完成1周内，乙方提请甲方组织现场验收，验收合格后1周内支付合同金额的97%，余款3%作为售后服务和质量保证金，自验收合格之日起满2年后10日内无息支付。    "]
["报价单位：                     乙方负责人签字确认：              日期："]